## Customer-Frontend
|  | Islamic Products |  | TC Start Date |  | TC Execution Start Date |  | TEST CASE SUMMARY
Module Name |  | Packages |  | TC End Date |  | TC Execution End Date |  | PASS |  |  | 18
Epic |  |  |  | Test Case Developed By | Rifat Tamanna | Browser (tested) | 1 | FAIL |  |  | 0
Developer Name (TL) |  | x |  | Test Case Reviewed By |  | Performance (tested) | No | WARNING |  |  | 0
Test Executed by | [7 empty] | TOTAL |  |  | 18
Test Case ID/Name | Module Name | Precondition | Test Case Description | Test Data | Test Steps Description | Expected Result | Actual Result | Status | Severity | Priority | Remarks | comment | Retest | Recheck Remark | Execution Date | Dev Status | Actual Time
Common Steps: -->Click on the website link
TC001 | Sign Up | https://ecom.excelitaiportfolio.com/ | go to Sign up page | N/A | --> hover on the right side person icon --> here 2 options open in dropdown sign in and sign up --> click on the sign up button | Open the sign up page | Open the sign up page | PASS | 1 | HIGH
TC002 | Sign Up | https://ecom.excelitaiportfolio.com/ | Verify "First name" | First name: <EMPTY> Last name: Smith email address: john Phone number:0123456789 password: 123456789 , Terms are agreed, | --> hover on the right side person icon --> here 2 options open in dropdown sign in and sign up --> click on the signup button ---> Input all the information --> click on the signup button | It would give a alert for the Empty First name field | It should give a alert for the Empty First name field | PASS | 1 | HIGH | Empty First name
TC003 | Sign Up | https://ecom.excelitaiportfolio.com/ | Verify "Last name" | First name: John Last name: <EMPTY> email address: john Phone number: 0123456789 password: 123456789 Terms are agreed, | -->Click on the website link --> hover on the right side person icon --> here 2 options open in dropdown sign in and sign up --> click on the signup button ---> Input all the information --> click on the signup button | It would give a alert for the Empty Last name field | It should not give any alert for the Empty Last name field | WARNING |  | LOW | Empty Last name
TC004 | Sign Up | https://ecom.excelitaiportfolio.com/ | Verify "Email ID" | First name: John Last name: Smith email address: john Phone number:0123456789 password: 123456789 , Terms are agreed, | -->Click on the website link --> hover on the right side person icon --> here 2 options open in dropdown sign in and sign up --> click on the signup button ---> Input all the information --> click on the signup button | It would give a alert for the invalid Email Address | It should give a alert for the invalid Email Address | PASS | 8 | HIGH | Invalid Email Address | [6 empty] | l | j
TC005 | Sign Up | https://ecom.excelitaiportfolio.com/ | Verify "Email ID" | First name: John Last name: Smith email address: john@ Phone number:0123456789 password: 123456789 , Terms are agreed, | --> click on the signup button ---> Input all the information --> click on the signup button | It would give a alert for the invalid Email Address | It should give a alert for the invalid Email Address | PASS | 8 | HIGH | Invalid Email Address | [6 empty] | l
TC006 | Sign Up | https://ecom.excelitaiportfolio.com/ | Verify "Phone number " | First name: John Last name: Smith email address: john@gmail.com Phone number:0123456789 password: 123456789 , Terms are agreed, | --> click on the sign up button ---> Input all the informations --> click on the sign up button | It would give a alert for the invalid phone number | Should not give any alert for invalid phone number, Sign up successfully | FAIL | 8 | HIGH | [7 empty] | j
TC007 | Sign Up | https://ecom.excelitaiportfolio.com/ | Verify "phone number country code " | First name: John Last name: Smith email address: john@gmail.com Phone number:0123456789 password: 123456789 , Terms are agreed, | --> click on the sign up button ---> Input all the information --> click on the signup button | For the specification purpose country code must be included with the phone number | Should not give any alert for input without country code | FAIL | 5 | HIGH | Without country code
TC008 | Sign Up | https://ecom.excelitaiportfolio.com/ | Verify "Email ID" | First name: John Last name: Smith email address: john Phone number:0123456789 password: 123456789 , Terms are agreed, | -->Click on the website link --> hover on the right side person icon --> here 2 options open in dropdown sign in and sign up --> click on the signup button ---> Input all the information --> click on the signup button | It would give a alert for the invalid Email Address | It should give a alert for the invalid Email Address | PASS | 8 | HIGH | Invalid Email Address | [6 empty] | l | j
TC009 | Sign Up | https://ecom.excelitaiportfolio.com/ | Verify "Email ID" | First name: John Last name: Smith email address: john@ Phone number:0123456789 password: 123456789 , Terms are agreed, | --> click on the signup button ---> Input all the information --> click on the signup button | It would give a alert for the invalid Email Address | It should give a alert for the invalid Email Address | PASS | 8 | HIGH | Invalid Email Address | [6 empty] | l
TC010 | Sign In | https://ecom.excelitaiportfolio.com/ | Verify" Email ID" and "Password" with "incorrect data" | Email Address/ Phone : John Password: 123456 | -->Click on the sign-in button --> input invalid values --> click on the sign in button | Give a alert for incorrect email and password | Give a alert for incorrect email and password | PASS |  | LOW | Invalid Email ID and Password
TC011 | Sign In | https://ecom.excelitaiportfolio.com/ | Verify with "Invalid email ID" and "Valid Password" | Email Address/ Phone : John Password: 123456789 | --> Click on the sign-in button --> input invalid values --> click on the sign in button | Give a alert for incorrect email Address | Give alert for incorrect email Address | PASS |  | LOW
TC012 | Sign In | https://ecom.excelitaiportfolio.com/ | Verify with "valid email Id" and "invalid Password" | Email Address/ Phone : John@gmail.com Password:12345 | -->Click on the sign-in button --> input invalid values --> click on the sign in button | Give a alert for incorrect Password | Give alert for incorrect password | PASS |  | LOW
TC013 | Sign In | https://ecom.excelitaiportfolio.com/ | Verify the text "No account Sign up now" | N/A | -->Click on the sign-in button --> input invalid values --> click on the sign in button | Should be new member registration text | Text does not be new member registration text | WARNING |  | LOW | New Member registration Text
TC014 | Sign In | https://ecom.excelitaiportfolio.com/ | Verify " Forget Password " button | N/A | -->Click on the sign-in button --> click on the forget password button | It should be redirected a forget password page were | It should be redirected a forget password page were | PASS |  | HIGH
TC015 | Sign In | https://ecom.excelitaiportfolio.com/ | Verify " Forget Password " button | N/A | -->Click on the sign in button --> click on the forget password button --> Open on Forget password page | If email ID and phone number are both for sign in then both will be for forget password | For foget password phone number input option does not included | FAIL |  | HIGH | forget password page- without phone number
TC016 | Sign In | https://ecom.excelitaiportfolio.com/ | Verify with "Invalid email ID and Valid Password" | Email Address/ Phone : John Password: 123456789 | --> Click on the sign-in button --> input invalid values --> click on the sign in button | Give a alert for incorrect email Address | Give alert for incorrect email Address | PASS |  | LOW
TC017 | Sign In | https://ecom.excelitaiportfolio.com/ | Verify with "valid email Id and invalid Password" | Email Address/ Phone : John@gmail.com Password:12345 | -->Click on the sign-in button --> input invalid values --> click on the sign in button | Give a alert for incorrect Password | Give alert for incorrect password | PASS |  | LOW
TC018 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "my profile" | N/A | -->Click on the dashboard button --> open on the user account page | Open on the profile page only | Open profile page with the update field | WARNING |  | LOW
TC019 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "Update First name" | First name: update "John" to "Jack" Last name: Smith email address: john Phone number:0123456789 password: 123456789 , Terms are agreed, | -->click on the dashboard button ---> input first name field from john to jack --> click on the update button | Update First name successfully | Update First name successfully | PASS |  | LOW | https://drive.google.com/file/d/1g5BiyirV7OpeVxOL5vS5WYe3-Uvf9hJB/view?usp=sharing
TC020 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "Update Last name" | First name: Jack Last name: "Smith" to "Sunny" email address: john Phone number:0123456789 password: 123456789 , Terms are agreed, | -->Click on the dashboard button --> input last name field from smith to sunny --> click on the update button | update Last name successfully | Update Last name successfully | PASS |  | LOW
TC021 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify " Update Email address " | First name: Jack Last name: "Smith" to "Sunny" email address: john Phone number:0123456789 password: 123456789 , Terms are agreed, | -->click on the dashboard button --> input the email address field | Update email address successfully | Input field into the email address field is blocked | FAIL |  |  | Email Address field block
TC022 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "Update password with old password" | First name: Jack Last name: "Smith" to "Sunny" email address: john Phone number:0123456789 password: update" 123456789 " to " 123456789 " , Terms are agreed, | --.Click on the dashboard button --> input the existing password to update the password | should give an alert for an old password , write a new password | Does not give any alert for using the same password for update the password, It would change password successfully | FAIL |  |  | update with same password
TC023 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "Update First name" | First name: update "John" to "Jack" Last name: Smith email address: john Phone number:0123456789 password: 123456789 , Terms are agreed, | -->click on the dashboard button ---> input first name field from john to jack --> click on the update button | Update First name successfully | Update First name successfully | PASS |  | LOW | https://drive.google.com/file/d/1g5BiyirV7OpeVxOL5vS5WYe3-Uvf9hJB/view?usp=sharing
TC024 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "Update password with a new password" | First name: Jack Last name: "Smith" to "Sunny" email address: john Phone number:0123456789 password: update" 123456789 " to " 123456 " , Terms are agreed, | -->Click on the dashboard button --> input the existing password for update password | Should update the password successfully | Should update the password successfully | PASS
TC026 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "Delete Account" Button | N/A | -->Click on the dashboard button --> click on the delete account button | Should give a alert for confirm delete the account | Should give a alert for confirm delete the account | PASS
TC027 | My profile | https://ecom.excelitaiportfolio.com/ | verify " Delete account--> no option " | N/A | -->Click on the dashboard button --> click on the delete account button --> click on the pop-up notification no button | Should not delete the account | Does not delete the account | PASS
TC028 | My profile | https://ecom.excelitaiportfolio.com/ | verify " Delete account--> Yes option " | N/A | -->Click on the dashboard button --> click on the delete account button --> click on the pop-up notification Yes button | Should delete the user account permanently | Should delete the user account permanently | PASS
TC029 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "Delete Account" Button | N/A | -->Click on the dashboard button --> click on the delete account button | Should give a alert for confirm delete the account | Should give a alert for confirm delete the account | PASS
TC030 | My profile | https://ecom.excelitaiportfolio.com/ | verify " Delete account--> no option " | N/A | -->Click on the dashboard button --> click on the delete account button --> click on the pop-up notification no button | Should not delete the account | Does not delete the account | PASS
TC031 | My order | https://ecom.excelitaiportfolio.com/account-oder | Verify" My order" page | N/A | -->click on the dashboard button --> click on the order button | Hash Sign would not be present after the order thext into the header column | Hash Sign would present after the order thext into the header column | FAIL |  |  | Hash icon present after order test
TC032 | My profile | https://ecom.excelitaiportfolio.com/user-account | verify "Delete Account" Button | N/A | -->Click on the dashboard button --> click on the delete account button | Should give a alert for confirm delete the account | Should give a alert for confirm delete the account | PASS
TC033 | My order | https://ecom.excelitaiportfolio.com/account-oder | Verify "View" Button | N/A | -->click on the dashboard button --> click on the view button | It should be redirect the order details page | It should be redirect the order details page | PASS
TC034 | My order | https://ecom.excelitaiportfolio.com/account-oder | Verify "Cancel" button | N/A | -->click on the dashboard button --> click on the view delete button | It should be cancel the product from the order list | It should be cancel the product from the order list | PASS
TC035 | My order | https://ecom.excelitaiportfolio.com/account-order-details?id=100041 | Verify " Review" button | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button | It should be redirect the order review page | It should redirect the order review page | PASS
TC036 | My order | https://ecom.excelitaiportfolio.com/submit-review/45 | Verify " Review " for the product | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button | It should be redirect the order review page | It should redirect the order review page | PASS
TC037 | My order | https://ecom.excelitaiportfolio.com/submit-review/45 | Verify " Rating " Option from the review page | Rating Select: 1 Rating Select: 2 Rating Select: 3 Rating Select: 4 Rating Select: 5 | --> click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> Select the options one by one | It should be select all the options properly | It should select all the options properly | PASS
TC038 | My order | https://ecom.excelitaiportfolio.com/submit-review/45 | Verify " Attachment " Option from the review page for a photo | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> Select the photo properly | Select a photo Successfully | Select a photo Successfully | PASS |  |  | Add photo
TC039 | My order | https://ecom.excelitaiportfolio.com/submit-review/45 | Verify " Attachment " Option from the review page for a file | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> Select the file properly | Select a file Successfully | Select a file Successfully | PASS
TC040 | My order | https://ecom.excelitaiportfolio.com/submit-review/45 | Verify " Submit" Option from the review page | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> click on the submit button | Submit the review successfully | Submit the review successfully | PASS
TC041 | My order | https://ecom.excelitaiportfolio.com/submit-review/45 | Verify " Back" Option from the review page | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> click on the back button | Back from the review successfully | Back from the review successfully | PASS
TC042 | My order | https://ecom.excelitaiportfolio.com/wallet | verify "My Wallet " section | N/A | --> click on the dashboard button --> click on the my order button --> click on the side bar my wallet button | Should open the wallet transaction history | Should have the wallet transaction history | PASS
TC043 | My order | https://ecom.excelitaiportfolio.com/loyalty | verify "My loyalty point"
TC044 | My order | https://ecom.excelitaiportfolio.com/account-oder | Verify "Track your order" | Order Id:100048 Phone number: 8801533853570 | --> Click on the dashboard button --> Click on my order button -->Click on the track your order -->Input all the values --> click on the track order button | Should be open the tracking order page | Should open the tracking order page | PASS
TC045 | My order | https://ecom.excelitaiportfolio.com/track-order/result | Verify "view order details " from the track order page | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the track your order --> Click on the view order details button | It should be open the ordered product details pop-up with the quantity , Tax, subtotal ,Coupon discount , Total price | It should open the ordered product details pop-up with the quantity , Tax, subtotal ,Coupon discount , Total price | PASS
TC046 | My order | https://ecom.excelitaiportfolio.com/wishlists | verify "Wishlist " | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the wish list button --> open a product page from wishlist --> Click on any product | Should be shown on the wishlist, open on the product details page and the add wishlist button would be colored for identifying that the product should be wishlisted | the add wishlist button should not colored for identifying that the product should be wishlisted | FAIL |  |  | Wishlist button
TC047 | My order | https://ecom.excelitaiportfolio.com/chat-with-seller | Verify" Chat with seller" | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the chat with seller button | Should be Open the seller chat box | Should open the seller chat box | PASS
TC048 | Sign up | https://ecom.excelitaiportfolio.com/customer/auth/sign-up | verify "sign up with google" button | N/A | -->Click on the sign up button --> click on the sign up with google button | Should be open the google sign up page | Should not open the google sign in page, it would give the 400 error | FAIL |  |  | sign up with google
TC049 | Sign up | https://ecom.excelitaiportfolio.com/customer/auth/sign-up | verify "sign up with facebook" button | N/A | -->Click on the sign up button --> click on the sign up with facebook button | Should be open the facebook sign up page | It contain the login error from facebook page | FAIL |  |  | sign up with facebook
TC050 | Sign In | https://ecom.excelitaiportfolio.com/customer/auth/login | verify "sign in with google" button | N/A | -->Click on the sign in button --> click on the sign in with google button | Should be open the google sign in page | Should not open the google sign in page, it would give the 400 error | FAIL |  |  | sign up with google
TC051 | Sign In | https://ecom.excelitaiportfolio.com/customer/auth/login | verify "sign in with facebook" button | N/A | -->Click on the sign in button --> click on the sign in with facebook button | Should be open the facebook sign in page | It contain the login error from facebook page | FAIL |  |  | sign up with facebook
TC052 | Sign up | https://ecom.excelitaiportfolio.com/customer/auth/sign-up | verify "Sign " spelling from sign up page | N/A | --> Click on the signup button | Sign spelling should be sign | It does not have sign spelled | FAIL |  |  | Spelling mistake in "sign"
TC053 | Profile Info | https://ecom.excelitaiportfolio.com/user-account | Verify " profile " page | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the profile info button | Should be open a profile page | Should open a profile page with edit option | FAIL |  |  | Profile view option
TC054 | Profile Info | https://ecom.excelitaiportfolio.com/user-account | Verify "New password " page | new Password: "using the same password which using before" | --> Click on the dashboard button --> Click on my order button -->Click on the profile info button --> input on the previous password into the new pass | Should be update with a new password | Should also update with a old password | FAIL |  |  | update with old password
TC055 | Address | https://ecom.excelitaiportfolio.com/account-address | Verify "Address" into the my order | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the address button | It should be open the previously added addresses into the page. | It should be open the previously added addresses into the page. | PASS
TC056 | Address | https://ecom.excelitaiportfolio.com/account-address | Verify "Add New Address" into the my order | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the address button -->click on the add new address button | It should be open a address form pop up | IT should be open a address form pop up | PASS
TC057 | Address | https://ecom.excelitaiportfolio.com/account-address | verify "address form" | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the address button -->click on the add new address button -->click on the fill all the input field | Here the map field should be a demo map view | Does not have the map present in add new address | FAIL |  |  | address map should not seen
TC058 | Address | https://ecom.excelitaiportfolio.com/account-address | verify "Zip code" field | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the address button -->click on the add new address button -->input the zip code field with infinity digit | It should be take only valid zip codes only | It contain unnecessary garbadge digits also | FAIL |  |  | Infinite digit zip code
TC059 | Address | https://ecom.excelitaiportfolio.com/account-address | verify "close" button | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the address button -->click on the add new address button --> click on the close button | When click on the close button it should be redirect on the address page | Close button does not work | FAIL |  |  | close button
TC060 | Address | https://ecom.excelitaiportfolio.com/account-address | verify "search box" | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the address button -->click on the add new address button --> click on the search box | Search map location or address or name | Does not work the search bar | FAIL |  |  | search box does not work
TC061 | Google Map Integration | https://ecom.excelitaiportfolio.com/admin/business-settings/web-config/mysitemap | Verify" Google Map Integration" | N/A | --> Click on the dashboard button --> Click on the generated sitemap -->click on the download sitemap button | Google Map Integration Missing | Google Map Integration Missing | FAIL
TC062 | Support Ticket | https://ecom.excelitaiportfolio.com/account-tickets | verify "Support ticket" | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the support ticket button | Submit a issue via the input field, Then it should be seen on the admin panel support ticket option | Submit a issue via the input field, Then it should seen on the admin panel support ticket option | PASS
TC063 | Support Ticket | https://ecom.excelitaiportfolio.com/admin/support-ticket/view | Verify" Support Ticket" | N/A | --> Click on the dashboard button --> Click on the support ticket | support ticket messeges should come properly | support ticket messeges should come properly | PASS |  |  | support ticket messeges
TC064 | product security for edit permission | https://ecom.excelitaiportfolio.com/seller/product/list | Verify " Product security issue" | N/A | --> Login on the seller dashboard -->click on the product button --> Copy the admin or other seller's product code --> paste it into the seller account product url | Security Problem: One seller can update the other seller/admin's product details. | Security Problem: One seller can update other seller/admin's product details. | FAIL |  |  | Product security issue
TC065 | Order/Cart/View | https://ecom.excelitaiportfolio.com/ | verify " Customers cart/view/order " | N/A | --> Login in with customer id | one customer can not view/change other customers's cart/orders etc. | one customer can not view/change other customers's cart/orders etc. | PASS
TC066 | Order | https://ecom.excelitaiportfolio.com/ | Verify " Customer address change" | N/A | -->Login into the coustomer, Seller at a time -->customer can order a product -->then customer can change their address --> then seller can processed the product | customer changes his addresses after order confirm, also send a alert into the admin and seller panel | customer changes his address after order confirm but no alert should sent into the admin or seller panel | FAIL |  |  | customer change their address after an order confirmed
TC067 | Order | https://ecom.excelitaiportfolio.com/ | Verify "Seller address Change" | N/A | -->Login into the customer, and seller panel at a glance -->customer can order a product -->then customer can change their address --> then seller can process the product | Seller changes his addresses after the order confirm | customer changes his address after order confirmed | FAIL
TC068 | Order | https://ecom.excelitaiportfolio.com/ | Verify "admin address Change" | N/A | -->Login into the coustomer, Seller and admin panel at a glance -->customer can order a product -->then customer can change their address --> then seller can processed the product | What happens id a customer changes his addresses after order confirm | What happens id a customer changes his addresses after order conifirm | FAIL |  |  | customer change their address after an order confirmed
TC069 | Check out page | https://ecom.excelitaiportfolio.com/checkout-details | Verify "Required field" | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the address button -->click on the add new address button | After fill all the required field then the save button would work | Without input any information save button does work | FAIL |  |  | Save the address button
Fixed

## Dashboard
|  |  |  | Islamic Products | TC Start Date |  | TC Execution Start Date |  | TEST CASE SUMMARY
| Module Name |  |  | Packages | TC End Date |  | TC Execution End Date |  | PASS |  |  | 0
| Epic |  |  |  | Test Case Developed By | Rifat Tamanna | Browser (tested) | 1 | FAIL |  |  | 0
| Developer Name (TL) |  |  | x | Test Case Reviewed By |  | Performance (tested) | No | WARNING |  |  | 0
| Test Executed by | [7 empty] | TOTAL |  |  | 0
version | Test Case ID/Name | Feature | Test Case Description | Precondition | Test Data | Step Description | Expected Result | Actual | Status | Severity | Priority | Remarks | comment | Retest | Recheck Remark | Execution Date | Dev Status | Actual Time
V#001 | TC001 | Customers | verify "Search by Email" | https://ecom.excelitaiportfolio.com/admin/customer/list | N/A | --> Login to the dashboard --> Click on the customers --> Search by the Email id | Result should be filtered by email id search | Result should filtered by email id search | PASS
V#001 | TC002 | Customers | verify "Search by Name" | https://ecom.excelitaiportfolio.com/admin/customer/list | N/A | --> Login to the dashboard --> Click on the customers --> Search by the Customer name | Result should be filtered by Name search | Result should filtered by Name search | PASS
V#001 | TC003 | Customers | verify "Search by Phone" | https://ecom.excelitaiportfolio.com/admin/customer/list | N/A | --> Login to the dashboard --> Click on the customers --> Search by the Customer Phone | Result should be filtered by Phone search | Result should filtered by Phone search | PASS
V#001 | TC004 | Customers | Verify" Block/Unblock" button | https://ecom.excelitaiportfolio.com/admin/customer/list | N/A | --> Login to the dashboard --> Click on the customers --> click on a Block button | Customer should be blocked for their login permission | Customer does not login at the blocked phase | PASS
V#001 | TC005 | Customers | Verify " Action" button | https://ecom.excelitaiportfolio.com/admin/customer/list | N/A | --> Login to the dashboard --> Click on the customers --> click on the view/ Action button | open on the order list into the customer | open on the order list into the customer | PASS
V#001 | TC006 | Customers--> Action | Verify " Search by order" | https://ecom.excelitaiportfolio.com/admin/customer/list | N/A | --> Login to the dashboard --> Click on the customers --> click on the view/ Action button -->click on the search bar --> Input any of the order id | Result should be filtered by order id search | Result should filtered by order id search | PASS
V#001 | TC007 | Customers--> Action | Verify " Search by order" | https://ecom.excelitaiportfolio.com/admin/customer/list | N/A | --> Login to the dashboard --> Click on the customers --> click on the view/ Action button -->click on the search bar --> Input any of the order id | Result should be filtered by order id search | Result should filtered by order id search | PASS
V#001 | TC008 | Customers--> Action--> single order page | Verify"order status change " | https://ecom.excelitaiportfolio.com/admin/customer/list | N/A | --> Login to the dashboard --> Click on the customers --> click on the view/ Action button -->go to the order details page --> Change the order status -->click on the back button | order status should be change into the view page | order status should not change into the view page | FAIL |  |  | order status should not change into the view page
V#001 | TC009 | Mail Config | Verify "Mail Integration" | https://ecom.excelitaiportfolio.com/admin/business-settings/mail | N/A | --> Login to the dashboard --> Click on the mail config -->input the test mail id --> click on the send mail button | Get a mail From the bppshop support mail id | Mail Intigrated properly | PASS |  |  | Mail Integration
v#1 | TC010 | Support Ticket | Verify" Support Ticket" | https://ecom.excelitaiportfolio.com/admin/support-ticket/view | N/A | --> Click on the dashboard button --> Click on the support ticket | On create Support ticket , no notification sent/viewed only after issue list page refreshing, the newly created issues can be viewed | On create Support issue, no notification sent/viewed only after issue list page refreshing, the newly created issues can be viewed | FAIL |  |  | support ticket issue
v#1 | TC011 | Google Map Integration | Verify" Google Map Integration" | https://ecom.excelitaiportfolio.com/admin/business-settings/web-config/mysitemap | N/A | --> Click on the dashboard button --> Click on the generated sitemap -->click on the download sitemap button | Google Map Integration Missing | Google Map Integration Missing | FAIL
v#1 | TC012 | Support Ticket | verify "Support ticket" | https://ecom.excelitaiportfolio.com/account-tickets | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the support ticket button | Submit a issue via the input field, Then it should be seen on the admin panel support ticket option | Submit a issue via the input field, Then it should seen on the admin panel support ticket option | PASS
| TC013 | Support Ticket | Verify" Support Ticket" | https://ecom.excelitaiportfolio.com/admin/support-ticket/view | N/A | --> Click on the dashboard button --> Click on the support ticket | support ticket messeges should come properly | support ticket messeges should come properly | PASS |  |  | support ticket messeges
v#1 | TC014 | product security for edit permission | Verify " Product security issue" | https://ecom.excelitaiportfolio.com/seller/product/list | N/A | --> Login on the seller dashboard -->click on the product button --> Copy the admin or other seller's product code --> paste it into the seller account product url | Security Problem: One seller can update the other seller/admin's product details. | Security Problem: One seller can update other seller/admin's product details. | FAIL |  |  | Product security issue
v#1 | TC015 | Order/Cart/View | verify " Customers cart/view/order " | https://ecom.excelitaiportfolio.com/ | N/A | --> Login in with customer id | one customer can not view/change other customers's cart/orders etc. | one customer can not view/change other customers's cart/orders etc. | PASS
v#1 | TC016 | Order | Verify " Customer address change" | https://ecom.excelitaiportfolio.com/ | N/A | -->Login into the coustomer, Seller at a time -->customer can order a product -->then customer can change their address --> then seller can processed the product | customer changes his addresses after order confirm, also send a alert into the admin and seller panel | customer changes his address after order confirm but no alert should sent into the admin or seller panel | FAIL |  |  | customer change their address after an order confirmed
v#1 | TC017 | Order | Verify "Seller address Change" | https://ecom.excelitaiportfolio.com/ | N/A | -->Login into the customer, and seller panel at a glance -->customer can order a product -->then customer can change their address --> then seller can process the product | Seller changes his addresses after the order confirm | customer changes his address after order confirmed | FAIL
v#1 | TC018 | Order | Verify "admin address Change" | https://ecom.excelitaiportfolio.com/ | N/A | -->Login into the coustomer, Seller and admin panel at a glance -->customer can order a product -->then customer can change their address --> then seller can processed the product | What happens id a customer changes his addresses after order confirm | What happens id a customer changes his addresses after order conifirm | FAIL |  |  | customer change their address after an order confirmed
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#2
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#2
v#1
v#1
v#2
v#1 | TC052
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#2
v#2
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1

## order
|  |  |  | Islamic Products | TC Start Date |  | TC Execution Start Date |  | TEST CASE SUMMARY
| Module Name |  |  | Packages | TC End Date |  | TC Execution End Date |  | PASS |  |  | 11
| Epic |  |  |  | Test Case Developed By | Rifat Tamanna | Browser (tested) | 1 | FAIL |  |  | 0
| Developer Name (TL) |  |  | x | Test Case Reviewed By |  | Performance (tested) | No | WARNING |  |  | 0
| Test Executed by | [7 empty] | TOTAL |  |  | 11
version | Test Case ID/Name | Feature | Test Case Description | Precondition | Test Data | Step Description | Expected Result | Actual | Status | Severity | Priority | Remarks | comment | Retest | Recheck Remark | Execution Date | Dev Status | Actual Time
v#1 | TC001 | My order | Verify" My order" page | https://ecom.excelitaiportfolio.com/account-oder | N/A | -->click on the dashboard button --> click on the order button | Hash Sign would not be present after the order thext into the header column | Hash Sign would present after the order thext into the header column | FAIL | LOW |  | Hash icon present after order test
v#1 | TC002 | My order | Verify "View" Button | https://ecom.excelitaiportfolio.com/account-oder | N/A | -->click on the dashboard button --> click on the view button | It should be redirect the order details page | It should be redirect the order details page | PASS
v#1 | TC003 | My order | Verify "Cancel" button | https://ecom.excelitaiportfolio.com/account-oder | N/A | -->click on the dashboard button --> click on the view delete button | It should be cancel the product from the order list | It should be cancel the product from the order list | PASS
v#1 | TC004 | My order | Verify " Review" button | https://ecom.excelitaiportfolio.com/account-order-details?id=100041 | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button | It should be redirect the order review page | It should redirect the order review page | PASS
v#1 | TC005 | Order (Dashboard) | verify " status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | should be shown the pending list for pending status | should be shown the pending list for pending status | PASS
v#1 | TC006 | Order (Dashboard) | verify " status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | should be shown the confirmed list for confirmed status | should be shown the confirmed list for confirmed status | PASS
v#1 | TC007 | Order (Dashboard) | verify " status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | should be shown the processing list for processing status | should be shown the processing list for processing status | PASS | [8 empty] | CRITICAL
v#1 | TC008 | Order (Dashboard) | verify " status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | should be shown the out for delivery list for out for delivery status | should be shown the out for delivery list for out for delivery status | PASS | [8 empty] | MAJOR
v#1 | TC009 | Order (Dashboard) | verify " status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | should be shown the delivered list for delivered status | should be shown the delivered list for delivered status | PASS | [8 empty] | MEDIUM
v#1 | TC010 | Order (Dashboard) | verify " status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | should be shown the returned list for returned status | should be shown the returned list for returned status | PASS | [8 empty] | LOW
v#1 | TC011 | Order (Dashboard) | verify " status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | should be shown the failed list for failed status | should be shown the failed list for failed status | PASS
v#1 | TC012 | My order | Verify " Review " for the product | https://ecom.excelitaiportfolio.com/submit-review/45 | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button | It should be redirect the order review page | It should redirect the order review page | PASS
v#1 | TC013 | My order | Verify " Rating " Option from the review page | https://ecom.excelitaiportfolio.com/submit-review/45 | Rating Select: 1 Rating Select: 2 Rating Select: 3 Rating Select: 4 Rating Select: 5 | --> click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> Select the options one by one | It should be select all the options properly | It should select all the options properly | PASS
v#1 | TC014 | My order | Verify " Attachment " Option from the review page for a photo | https://ecom.excelitaiportfolio.com/submit-review/45 | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> Select the photo properly | Select a photo Successfully | Select a photo Successfully | PASS |  |  | Add photo
v#1 | TC015 | My order | Verify " Attachment " Option from the review page for a file | https://ecom.excelitaiportfolio.com/submit-review/45 | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> Select the file properly | Select a file Successfully | Select a file Successfully | PASS
v#1 | TC016 | My order | Verify " Submit" Option from the review page | https://ecom.excelitaiportfolio.com/submit-review/45 | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> click on the submit button | Submit the review successfully | Submit the review successfully | PASS
v#1 | TC017 | My order | Verify " Back" Option from the review page | https://ecom.excelitaiportfolio.com/submit-review/45 | N/A | -->click on the dashboard button --> click on the view button --> click on the product review button --> Click on the rating option --> click on the back button | Back from the review successfully | Back from the review successfully | PASS
v#2 | TC018 | My order | verify "My Wallet " section | https://ecom.excelitaiportfolio.com/wallet | N/A | --> click on the dashboard button --> click on the my order button --> click on the side bar my wallet button | Should open the wallet transaction history | Should have the wallet transaction history | PASS
v#1 | TC020 | My order | verify "My loyalty point" | https://ecom.excelitaiportfolio.com/loyalty | [6 empty] | Need discussion
v#1 | TC021 | My order | Verify "Track your order" | https://ecom.excelitaiportfolio.com/account-oder | Order Id:100048 Phone number: 8801533853570 | --> Click on the dashboard button --> Click on my order button -->Click on the track your order -->Input all the values --> click on the track order button | Should be open the tracking order page | Should open the tracking order page | PASS
v#1 | TC022 | My order | Verify "view order details " from the track order page | https://ecom.excelitaiportfolio.com/track-order/result | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the track your order --> Click on the view order details button | It should be open the ordered product details pop-up with the quantity , Tax, subtotal ,Coupon discount , Total price | It should open the ordered product details pop-up with the quantity , Tax, subtotal ,Coupon discount , Total price | PASS
v#1 | TC023 | My order | verify "Wishlist " | https://ecom.excelitaiportfolio.com/wishlists | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the wish list button --> open a product page from wishlist --> Click on any product | Should be shown on the wishlist, open on the product details page and the add wishlist button would be colored for identifying that the product should be wishlisted | the add wishlist button should not colored for identifying that the product should be wishlisted | FAIL |  |  | Wishlist button
v#1 | TC024 | My order | Verify" Chat with seller" | https://ecom.excelitaiportfolio.com/chat-with-seller | N/A | --> Click on the dashboard button --> Click on my order button -->Click on the chat with seller button | Should be Open the seller chat box | Should open the seller chat box | PASS
v#1 | TC025 | Order/Cart/View | verify " Customers cart/view/order " | https://ecom.excelitaiportfolio.com/ | N/A | --> Login in with customer id | one customer can not view/change other customers's cart/orders etc. | one customer can not view/change other customers's cart/orders etc. | PASS
v#1 | TC026 | Order | Verify " Customer address change" | https://ecom.excelitaiportfolio.com/ | N/A | -->Login into the coustomer, Seller at a time -->customer can order a product -->then customer can change their address --> then seller can processed the product | customer changes his addresses after order confirm, also send a alert into the admin and seller panel | customer changes his address after order confirm but no alert should sent into the admin or seller panel | FAIL | MEDIUM | HIGH | customer change their address after an order confirmed
v#1 | TC027 | Order | Verify "Seller address Change" | https://ecom.excelitaiportfolio.com/ | N/A | -->Login into the customer, and seller panel at a glance -->customer can order a product -->then customer can change their address --> then seller can process the product | Seller changes his addresses after the order confirm | customer changes his address after order confirmed | FAIL | MEDIUM | HIGH
v#1 | TC028 | Order | Verify "admin address Change" | https://ecom.excelitaiportfolio.com/ | N/A | -->Login into the coustomer, Seller and admin panel at a glance -->customer can order a product -->then customer can change their address --> then seller can processed the product | What happens id a customer changes his addresses after order confirm | What happens id a customer changes his addresses after order conifirm | FAIL | MEDIUM | MEDIUM | customer change their address after an order confirmed
v#1 | TC029 | All Order list (Dashboard) | Verify "Search bar and filter" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Click on the dashboard button --> Click on order list | should be search and filter option work at a time | should not be search and filter option work at a time | FAIL | LOW | LOW | Search and filter
v#1 | TC030 | All Order list (Dashboard) | Verify "Order Id from seller and admin " | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login in into the admin and seller dashboard --> click on the order list --> from seller an order id would track for the admin panel | Should be the same information into the both admin and seller panel | Should be the same information into the both admin and seller panel | PASS
| TC031 | All Order list (Dashboard) | Verify "Order details page variation" button | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel --> Click on the order button --> click any order id to details view -->click on the variation button | How to work on the variation button | How to work on the variation button | FAIL | MEDIUM | Need discussion | variation button
v#1 | TC032 | All Order list (Dashboard) | verify " order show location map" button | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id | Loation map should be shown when click on the show location map button | Location data should not found | FAIL | MAJOR | HIGH | Location data
v#1 | TC033 | All Order list (Dashboard) | Verify "Print invoice option" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id -->click on the print invoice button | Should be open print option or download the pdf that printable | should open print option or download the pdf that printable | PASS
v#1 | TC034 | All Order list (Dashboard) | verify "Linked orders from the order detalis page" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id -->click on the print invoice button | How to work on the linked orders , By clicking on the ID it would go to 10052 ID details page | How to work on the linked orders , By clicking on the ID it would go to 10052 ID details page | FAIL |  |  | Linked orders
v#1 | TC035 | All Order list (Dashboard) | verify choose "By thirt party delivery service " option for shipment | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id -->click on the "choose delivery type" dropdown --> choose "By thirt party delivery service" --> Add delivery service name "Invalid" --> Add tracking id "Invalild" | Delivery service name and tracking id should be taken vaild data only | Delivery service name and tracking id does not vaild | FAIL |  |  | Delivery service name and tracking id
v#1 | TC036 | Order (Dashboard) | verify " Payment status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | should be shown the unpaid list for unpaid payment status | should be shown the unpaid list for unpaid payment status | PASS
v#1 | TC037 | Order (Dashboard) | verify "By self delivery man" option for shipment | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id -->click on the "choose delivery type" dropdown --> choose "By self delivery man" | After select a delivery man the other delivery man name should not be selectable mood into the dropdown | After select a delivery man, when click on the other delivery man name it also select the other delivery man | FAIL | LOW | LOW | Select randomly delivery man
| TC038 | Order (Dashboard) | verify " Shipping method" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id -->click on the "choose delivery type" dropdown --> choose "By thirt party delivery service" | If select shipping method in company vehicle then how the thirt party service should deliver the parcel | If select shipping method in company vehicle then how the thirt party service should deliver the parcel | FAIL |  |  | shipping method
v#1 | TC039 | Order (Dashboard) | verify choose "By thirt party delivery service " option for shipment | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id -->click on the "choose delivery type" dropdown --> choose "By thirt party delivery service" | Delivery servicew name should not be contain blank | Delivery service name should not conatain blank value | PASS
v#1 | TC040 | Order (Dashboard) | verify choose "By thirt party delivery service " option for shipment | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id -->click on the "choose delivery type" dropdown --> choose "By thirt party delivery service" | Update the delivery service name and tracking id with using different data, do not update for same data , it should be given an alert for same data | delivery service name and tracking id update with new value | FAIL | MAJOR | MEDIUM | update with same data
v#1 | TC041 | Order (Dashboard) | Verify "icon beside the store name" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the "order" button -->click any order id | Icon should open the seller information | Icon should open the seller information | PASS |  |  | icon
v#1 | TC042 | Order (Dashboard) | verify "change order status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the "order" button -->click any order id | After changing the status from confirming to processing it should not be editable for pending and confirmed mood | After change the status from confirm to processing it also editable for pending and confirmed mood | FAIL | MAJOR | HIGH | validation to changing status
v#2 | TC043 | Order (Dashboard) | verify "paid and unpaid option" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id | once select paid option it should not be edit with unpaid option | Once the paid option is selected, the unpaid option can also be selected | FAIL | MEDIUM | MEDIUM | update paid to unpaid
v#1 | TC044 | Order (Dashboard) | verify "change paid and unpaid option" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id | When the status changes from Unpaid to Paid, the status below the order changes | When the status changes from Unpaid to Paid, the status below the order changes | FAIL | MAJOR | MEDIUM | status should not change
v#1 | TC045 | Order (Dashboard) | Verify "Billing address" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id | how receive cash without delivery address | how receive cash without delivery address | FAIL | MEDIUM | MEDIUM | how receive cash without delivery address
v#1 | TC046 | Order (Dashboard) | Verify "canceled order paid status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id | How to change the paid status of a canceled order | How to change the paid status of a canceled order | FAIL | MAJOR | MEDIUM | How to change the paid status of a canceled order
v#1 | TC047 | Order (Dashboard) | verify "Shipping address" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id | Shipping address and phone number should be valid | Shipping address and phone number should be valid | FAIL | MAJOR | HIGH | Shipping address and phone number should be valid
v#1 | TC048 | Order (Dashboard) | verify "Cash on delivery method for paid order" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id | How to pay order for cash on delivery | How to pay order for cash on delivery | FAIL | MEDIUM | MEDIUM | how to pay order for cash on delivery
v#1 | TC049 | Order (Dashboard) | go to "Failed order status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button -->click any order id | How to work the failed order status | How to work the failed order status | FAIL | MEDIUM | MEDIUM
v#1 | TC050 | Order (Dashboard) | verify " Inhouse only button" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button | after click on the inhouse only button it should be filtered on only inhouse orders only | after click on the inhouse only button it should be filtered on only inhouse orders only | PASS
| TC051 | Order (Dashboard) | verify "unpaid payment order status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the order button --Click on the payment status on unpaid --> then click on the order status in delivered | The status Should not change delivered with unpaid status | The status Should not change delivered with unpaid status | PASS
v#1 | TC052 | Order transaction | Verify "Search bar" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the "Order transaction" Button | should be search properly | should search properly | PASS
v#1 | TC053 | Order transaction | verify " select customer" filter | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the "Order transaction" Button --> Select the preferred customer name | Should be filter with customer name properly | Should filter with customer name properly | PASS
v#1 | TC054 | Order transaction | verify "Select status" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the "Order transaction" Button -->Select the status from the dropdown | Should be filter with status properly | Should filter with status properly | PASS
v#1 | TC055 | Order transaction | verify "Date filter" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the "Order transaction" Button --> click on the calendar option and select the date --> Click on the filter button | Should be filter with preferred date properly | Should be filter with preferred date properly | PASS
v#1 | TC056 | Order transaction | verify "Export " button | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the "Order transaction" Button --> Click on the export option | Should be export file properly | Should be export file properly | PASS
v#1 | TC057 | Order (Dashboard) | verify" order date " from order details page | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel -->click on the "Order" Button | how was the order date should work, Is their any alert should be given for lengthy delivery | how was the order date should work, Is their any alert should be given for lengthy delivery | FAIL | MEDIUM | MEDIUM | delivery date issue
| TC058 | Order (Dashboard) | verify "order panel statistics search bar" | https://ecom.excelitaiportfolio.com/admin/auth/login | N/A | --> Login on the admin panel --> Login on the seller panel -->click on the order button from the sidebar | For seller dashboard statistics search would present but for admin dashboard no statistics search would present here | For seller dashboard statistics search would present but for admin dashboard no statistics search would present here | FAIL | LOW | LOW | statistics search bar
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#2
v#2
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1
v#1 | [9 empty] | LOW
v#1